## Slide 1: 1st Puerto Rico Organic Recycling Summit
Handling of Vegetative Debris after Hurricane Maria
Terra Campestre, Guaynabo, Puerto Rico
May 18, 2018

## Slide 2: Handling of Vegetative Debris after Hurricane Maria Hurricanes Data Comparison
Hurricane Georges /1998
Category: 3 Hurricane
Sustained Winds: 115 MPH
Wind Gust of: 150 MPH
Hurricane Maria /2017
Category: 4-5 Hurricane
Sustained Winds: 150 MPH
Wind Gust of: 185 MPH
Information gathered showed that at Guayama, AES facility Wind Gust were measured at 200 MPH

## Slide 3: Handling of Vegetative Debris after Hurricane Maria Hurricanes Path Through Puerto Rico
Hurricane Georges /1998
Hurricane Maria /2017

## Slide 4: Handling of Vegetative Debris after Hurricane Maria
Municipalities in Green Received more than 100,000 cy of Debris
Toa Baja Received more than 200,000 cy
Ponce Received More than 300,000 cy
Data does not considers Municipalities of San Juan, Bayamón and others not handled by the USACE

## Slide 5: Handling of Vegetative Debris after Hurricane Maria
Operational Data As of May 14, 2018
  Approximately 4.0 MM cy of debris collected and Processed,
    Approx. 1.92 MM cy of Vegetative Debris
    Approx. 2.06 MM cy of Const. & Demolition Debris.
  Approx. 100,000 cy of Landslide Material Handled,
  Approx. 345,000 cy of Non-Recyclable Mixed Vegetation,
  Around 34,000 cy of Hardwoods,
  A total of 179,626 debris loads handled
  Total of 1,672 USACE Certified Trucks
Background Information

## Slide 6: Handling of Vegetative Debris after Hurricane Maria
Goal Reached
4,000,000 cy
Debris Managed
May 17, 2018

## Slide 7: Handling of Vegetative Debris after Hurricane Maria
State Listed Temporary Debris Reduction Sites

## Slide 8: Handling of Vegetative Debris after Hurricane Maria
State Listed Temporary Debris Reduction Sites (TDRS):
Most of them didn't complied with the FEMA/ USACE Environmental Requirements:
Located in Flood Prone Areas,
Located within listed Wetlands Areas,
Did not showed the required area to undertake a TDRS operation with the required safety setback distances,
Access roads were no adequate to sustain the TDRS operations.
These situations forced the FEMA / USACE to undertake an Fastrack Evaluation of sites where the TDRS could be located and at the same time, secure the Required State and Federal Permits needed for its operations

## Slide 9: Handling of Vegetative Debris after Hurricane Maria Debris Management Challenges
DUE to the LIMITATION of adequate TDRS Sites, the USACE was force to undertake the Following Work Plan:
Initiate the Collection and Hauling of the Accumulated C&D Debris at the Right of Way to the Approved Landfills, (Two weeks after the Event)
Vegetative Debris was collected One Months after the Hurricane Event, allowing for its natural decomposition.

## Slide 10: Handling of Vegetative Debris after Hurricane Maria
To comply with ALL Environmental Requirements the following steps needs to be up-dated in the Puerto Rico Emergency Work Plan :
Develop a standardized Permit Application Forms that could be utilized that is approved by all Stake holders,
Facilitate alternatives access options under which the GIS Data Bank required for the completion of the Sites Initial Environmental Evaluation Procedure could be available.
Establish a Pre-Disaster Work Plan where all state holders are fully aware of its contribution and responsibilities,
Operations Areas should be preliminary established as part of the PR Disaster Work Plan in order to facilitate the Implementation of the Debris Removal and processing efforts. Six (6) Areas were designated to cope with Hurricane Maria Mission.
NEPA & Environmental Policy Act Compliance Requirements

## Slide 11: Handling of Vegetative Debris after Hurricane Maria TDRS / Mulch Farm Sites Permit Process Steps
Hurricane Georges /1998
Blanket Waiver Order Issued by the Environmental Quality Board (EQB) covering the operation of all TDRS sites.
Time Required for Permit Approval: 1 day
Vegetative Debris Hauling and Reduction Efforts were initiated 5 days after Georges Hurricane Event
No Site Inspection Required
Hurricane Maria /2017
Secure an EQB Operation Waiver to operate a TDRS, Debris Transport (DS-1), and Final Disposal Sites,
File a NEPA Compliance Permit Application before FEMA requiring endorsements from: (1) EPA, (2) SHIPO, (3) USFWS , (4) Forest Services (If Applicable) (5) Other Federal Agencies.
Mandatory Site Inspection
Time Required for Permit Approval: 5 day
Vegetative Debris Reduction Efforts were initiated 35 days after Maria Hurricane Event

## Slide 12: Handling of Vegetative Debris after Hurricane Maria Available Debris Infrastructure
Hurricane Georges /1998
Landfills in Operation: 32 Sites
Composting Facilities: 1 Site (Arecibo)
Grinders Available (SWMA): 5 Units
TDRS Sites: 1 at LMM Park
Mulch Material delivered to the SJ Municipal Landfill for Daily Coverage
Hurricane Maria /2017
Approved EQB Landfills : 13 Sites
Composting Facilities: 4 Commercial Sites
Grinders Available: 11 Units plus 4 additional on private hands (Total of 15 Units),
TDRS Sites: 9 operated under USACE, plus others handled by Individual Municipalities
Mulch Material delivered to the 13 EQB Approved Landfills for Daily Coverage, plus to 18 Agricultural Farms
TDRS & Farms Sites must be Readily Available and Pre-Approved as part of the PR Disaster Work Plan

## Slide 13: Handling of Vegetative Debris after Hurricane Maria
Hauling and Processing the 1.92 MM cy of Vegetative Debris received at the TDRS
Once Vegetative Debris Material was hauled:
  Significant portion of vegetative debris was mixed with C&D material limiting its re-utilization capabilities and forcing us to haul said material to one of the Approved Landfills, (345,000 cy)
  Reduction Rates of Grinded Debris was less than established by FEMA Operations Manual
  Soil was mixed with the Vegetative Debris forcing us to utilize Power Screens Units.
  Over 900,000 cy of Vegetative Debris was beneficially re-utilized.
Factors that Limited the Beneficial Reutilization of Vegetative Debris

## Slide 14: Handling of Vegetative Debris after Hurricane Maria Lessons Learned & Recommended Updates in the State Disaster Work Plan
PRE-APPROVED Temporary Debris Reduction Sites (TDRS) and Potential Composting / Agricultural Farms meeting FEMA / EQB regulatory Requirements,
Develop a standardized Joint Permit Application Forms that could be utilized at all State & Federal Regulatory Agencies,
Facilitate options under which the GIS Data Bank required for the completion of the Initial Environmental Evaluation efforts could be available.
Establish a Pre-Disaster Work Plan where all state holders are fully aware of its contribution and responsibilities,
Negotiate Disposal and Re-Utilization fees covering all products to be handled,

## Slide 15: Handling of Vegetative Debris after Hurricane Maria Lessons Learned & Recommended Updates in the State Disaster Work Plan
  By Pre-approving the TDRS / Mulch Re-utilization Farms before the Disaster Event, Debris Hauling and Processing Efforts related with the Debris Mission could be initiated faster and the work load of the FEMA / EQB personnel will be completed faster.
  Educate all Parties involved on the importance of collecting all vegetative debris as cleaned as possible, (This will increase our Vegetative material Re-utilization Rate over 50%),
  Incorporate the utilization of Power Screens Units as part of the operational and gridding equipment Set-Up.
  THANKS FOR THE INVITATION TO THE
  1st Puerto Rico Organic Recycling Submit
  Eng. Danny Pagan, PE